## Slide 2: Where We Are Now

## Slide 3: Developing the Project Plan
The Project Network
  A flow chart that graphically depicts the sequence, interdependencies, and start and finish times of the project job plan of activities that is the critical path through the network.
    Provides the basis for scheduling labor and equipment.
    Enhances communication among project participants.
    Provides an estimate of the project’s duration.
    Identifies activities that are critical.
    Highlights activities that are “critical” and can not be delayed.
    Help managers get and stay on plan.

## Slide 4: Constructing a Project Network
Terminology
  Activity: an element of the project that requires time.
  Merge Activity: an activity that has two or more preceding activities on which it depends.
  Parallel (Concurrent) Activities: Activities that can occur independently and, if desired, not at the same time.
A
C
D
B

## Slide 5: Constructing a Project Network (cont’d)
Terminology
  Path: a sequence of connected, dependent activities.
  Critical path: the longest path through the activity network that allows for the completion of all project-related activities; the shortest expected time in which the entire project can be completed. Delays on the critical path will delay completion of the entire project.
A
B
D
(Assumes that minimum of A + B > minimum of C in length of times to complete activities.)
C

## Slide 6: Constructing a Project Network (cont’d)
Terminology
  Event: a point in time when an activity is started or completed. It does not consume time.
  Burst Activity: an activity that has more than one activity immediately following it (more than one dependency arrow flowing from it).
Two Approaches
  Activity-on-Node (AON)
    Uses a node to depict an activity.
  Activity-on-Arrow (AOA)
    Uses an arrow to depict an activity.
B
D
A
C

## Slide 7: Basic Rules to Follow in Developing Project Networks
Networks typically flow from left to right.
An activity cannot begin until all preceding connected activities are complete.
Arrows indicate precedence and flow and can cross over each other.
Each activity must have a unique identify number that is greater than any of its predecessor activities.
Looping is not allowed.
Conditional statements are not allowed.
Use common start and stop nodes.

## Slide 8: Network Computation Process
Forward Pass—Earliest Times
  How soon can the activity start? (early start—ES)
  How soon can the activity finish? (early finish—EF)
  How soon can the project finish? (expected time—ET)
Backward Pass—Latest Times
  How late can the activity start? (late start—LS)
  How late can the activity finish? (late finish—LF)
  Which activities represent the critical path?
  How long can activity be delayed? (slack or float—SL)

## Slide 9: Forward Pass Computation
Add activity times along each path in the network (ES + Duration = EF).
Carry the early finish (EF) to the next activity where it becomes its early start (ES) unless…
The next succeeding activity is a merge activity, in which case the largest EF of all preceding activities is selected.

## Slide 10: Backward Pass Computation
Subtract activity times along each path in the network (LF - Duration = LS).
Carry the late start (LS) to the next activity where it becomes its late finish (LF) unless
The next succeeding activity is a burst activity, in which case the smallest LF of all preceding activities is selected.

## Slide 11: Determining Free Slack (or Float)
Free Slack (or Float)
  Is the amount of time an activity can be delayed after the start of a longer parallel activity or activities.
  Is how long an activity can exceed its early finish date without affecting early start dates of any successor(s).
  Allows flexibility in scheduling scarce resources.
Sensitivity
  The likelihood the original critical path(s) will change once the project is initiated.
  The critical path is the network path(s) that has (have) the least slack in common.

## Slide 12: Practical Considerations
Network Logic Errors
Activity Numbering
Use of Computers to Develop Networks
Calendar Dates
Multiple Starts and Multiple Projects

## Slide 13: Extended Network Techniques to Come Close to Reality
Laddering
  Activities are broken into segments so the following activity can begin sooner and not delay the work.
Lags
  The minimum amount of time a dependent activity must be delayed to begin or end.
    Lengthy activities are broken down to reduce the delay in the start of successor activities.
    Lags can be used to constrain finish-to-start, start-to-start, finish-to-finish, start-to-finish, or combination relationships.

## Slide 14: Hammock Activities
Hammock Activity
  Spans over a segment of a project.
  Has a duration that is determined after the network plan is drawn.
  Is used to aggregate sections of the project to facilitate getting the right amount of detail for specific sections of a project.
  Is very useful in assigning and controlling indirect project costs.

## Slide 15: Key Terms
Activity
Activity-on-arrow (AOA)
Activity-on-node (AON)
Burst activity
Concurrent engineering
Critical path
Early and late times
Free slack
Gantt chart
Hammock activity
Lag relationship
Merge activity
Parallel activity
Sensitivity
Total slack