COMSATS University Islamabad, Lahore.

Submitted to:

Tahir Aziz Khan

Submitted by:

Omama Mukhtar  FA22-BCE-051

Maryam Asif         FA22-BCE-014

Junaid Zaheer      FA22-BCE-045

Aliyan Ahmed      FA22-BCE-028

Statement of Work (SOW)

Project title: AI-Driven Non-Invasive Glucose Monitoring System.

Purpose / Background: Replace painful finger-prick tests with a wearable PPG-based non-invasive glucose monitor, combine signal processing + ML to estimate glucose, and provide an IoT/cloud dashboard + chatbot to support patients and doctors.

Scope :

- Design and build a working PPG sensor prototype (sensor + microcontroller + enclosure).

- Acquire and preprocess PPG signals; implement noise & motion-artifact handling; extract morphological/temporal/frequency features.

- Train, validate and select ML models (classical regressors and time-series DL e.g., LSTM) to map PPG features → glucose estimates.

- Build a secure IoT pipeline (device → cloud), implement alert engine for abnormal glycemic events.

- Develop web + mobile dashboard and an integrated AI chatbot for patient guidance and doctor–patient communication.

- End-to-end integration, system testing, documentation, final report and demonstration.

Explicit exclusions:

- Regulatory approvals / medical device certification.

- Long-term clinical trials beyond proof-of-concept/controlled validation with consenting volunteers.

- Integration with third-party commercial EHR systems unless explicitly requested.

Deliverables :

- Hardware prototype (PPG device).

- ML model trained & validated on PPG dataset.

- IoT cloud backend with secure data handling and alerts.

- Web/mobile dashboard + integrated chatbot for patients & doctors.

- Final report, user manual, demo slides and source code package.

Acceptance criteria:

- Hardware: device must stream stable PPG data to the microcontroller and cloud, and function for demo.

- Data / ML: model produces repeatable predictions and evaluation results reported (train/val/test metrics, and error analysis). Aim to demonstrate clinically-relevant performance (report Clarke Error Grid or equivalent + MAE/MARD metrics).

- Software: cloud APIs functional; dashboard shows real-time trends, history, alerts; chatbot responds to basic guidance flows.

- Documentation: final report includes architecture diagrams, dataset collection notes, code repo link, and testing logs.

Constraints & assumptions:

Access to basic hardware (PPG sensor modules, STM32/ESP32/Arduino, cables) and a few volunteer subjects for controlled data collection.

Internet/cloud account (Firebase/AWS or similar) for backend.

Change control: All scope changes are to be approved by the supervisor (Dr. Jehangir Arshad) and documented in a change log.

Project Charter

Project name: AI-Driven Non-Invasive Glucose Monitoring System.

Project sponsor / supervisors:

Supervisor: Dr. Jehangir Arshad.

Co-supervisor: Dr. Arsla Khan.

Project manager / owner: Omama Mukhtar, Maryam Asif, Junaid Zaheer, Aliyan Ahmed.

Objective (executive summary):

- Build a proof-of-concept PPG wearable + ML/cloud pipeline and dashboard that estimates glucose non-invasively and provides alerts + basic doctor-patient tools.

- Success criteria: Successful demo of (1) streaming PPG prototype, (2) ML model with validated metrics reported, (3) working IoT/cloud pipeline with alerts, and (4) usable dashboard/chatbot. Final report & code submitted.

- Key stakeholders: Supervisor & co-supervisor; student team; volunteer subjects (data); university examiners.

Milestones :

M1 – Requirements & detailed design (sensors, microcontroller, data schema).

M2 – Hardware prototype & initial PPG acquisition.

M3 – Data collection & preprocessing pipeline.

M4 – Model training & validation.

M5 – Cloud backend + alert engine.

M6 – Dashboard + chatbot.

M7 – Integration, system testing, final report & demo.

High-level risks & mitigation:

Risk: Motion / noise in PPG data hurts model quality → Mitigation: robust preprocessing + collect more controlled samples & augmentations.

Risk: Hardware sensor reliability → Mitigation: test multiple sensors/modules, add mechanical fixture to reduce pressure variation.

Risk: Insufficient labeled data (ground truth glucose) → Mitigation: small controlled collection with finger-prick references or public datasets for prototyping.

Budget (high-level): student to estimate hardware & cloud costs (sensors, microcontroller, PCB/3D printing, cloud hosting). (Not provided in the proposal; add numbers as needed.)

Approval: (signature lines) Project manager / Supervisor / Co-supervisor.

Work Breakdown Structure (WBS)

Top-level WBS (deliverable-oriented). I use WBS codes; you can paste this into your report or project plan.

1.0 Project Management & Admin

1.1 Kickoff & charter finalization

1.2 Weekly supervisor meetings (Mon & Fri) & status reports.

1.3 Change log & risk register

2.0 Requirements & System Design

2.1 Review literature & select sensors (PPG + optional BIS).

2.2 Define functional & non-functional requirements (data rates, security, performance)

2.3 Architecture diagrams & data flow (device → MCU → cloud → dashboard).

3.0 Hardware Development

3.1 Procure PPG sensors & microcontroller (STM32/ESP32/Arduino).

3.2 Prototype circuitry & breadboard tests

3.3 PCB / enclosure design (optional)

3.4 Device firmware: ADC sampling, basic filtering, secure comms

4.0 Data Acquisition & Processing

4.1 Controlled data collection planning (consent forms, protocol)

4.2 Signal acquisition runs (collect PPG + ground truth glucose where possible)

4.3 Preprocessing: filtering, motion artifact removal, segmentation

4.4 Feature extraction: morphological, temporal, spectral features.

5.0 Machine Learning Development

5.1 Exploratory data analysis & baseline models (RandomForest, SVM).

5.2 Time-series / DL (LSTM/RNN) experiments

5.3 Model selection, hyperparameter tuning & cross-validation

5.4 Model explainability & error analysis

6.0 IoT & Cloud Backend

6.1 Select cloud stack (Firebase/AWS) & DB schema.

6.2 Device ↔ cloud secure API implementation (HTTPS, auth)

6.3 Alert engine & notification service

6.4 Model deployment in cloud (inference endpoint)

7.0 Dashboard & Chatbot

7.1 UI/UX wireframes for web & mobile

7.2 Frontend implementation (real-time charts, history, alerts)

7.3 Chatbot flows and integration (basic advice + links to data)

7.4 User management & doctor–patient features

8.0 Integration & Testing

8.1 Unit tests (firmware, APIs, ML)

8.2 Integration tests (device → cloud → dashboard)

8.3 System validation & demo preparation

9.0 Documentation, Report & Final Delivery

9.1 Final report & code repository

9.2 User manual and presentation slides

9.3 Demo & viva preparation

Acceptance/checkpoints: At the end of each phase the team demonstrates the phase artifacts (e.g., prototype demo after 3.0, training results after 5.0, integrated demo after 8.0).

Organizational Breakdown Structure (OBS)

Below is a compact OBS (roles) and a RACI mapping for the top-level WBS items.

OBS (roles & responsibilities):

Project Supervisor (Dr. Jehangir Arshad) — oversight, approvals, technical guidance, milestone acceptance.

Co-Supervisor (Dr. Arsla Khan) — technical review, testing guidance, domain input.

Project Manager (group members)— overall delivery, schedule, integration, reporting.

Hardware Lead — sensor selection, firmware, prototype build.

ML Lead — data pipeline, modelling, validation.

Backend Developer — cloud APIs, model deployment, alert engine.

Frontend Developer / UI — dashboard & chatbot UI.

Data Collection Lead — experimental protocol, consent, data labeling.

QA & Documentation — testing, final report, slides, user manual.